## Slide 1: NASA EVA Gamification
Group 3
Prepared By
Michael Salgo
Victoria Guadagno
Okechukwu Ogudebe
Jacqueline Macfadyen
Kevin Fortier
02/18/2018
Notes: [Michael Salgo]
Good afternoon, Dr. Brown.
Thank you for taking the time to join us today. Today on the call we have myself (Michael Salgo), Victoria Guadagno, Jacqueline Macfadyen, and Kevin Fortier and we will be presenting our group 3 Project Plan on NASA EVA Gamification.

## Slide 2: Project Sponsor/Liaison
Sponsor
Extra-Vehicular Activity (EVA), Johnson Space Center, NASA
Liaison
Daren Welsh, EVA Instructor & Flight Controller
  darenwelsh@gmail.com
Notes: Our group 3 project sponsor is Extra-Vehicular Activity (EVA), Johnson Space Center, NASA (the division handling space walks and other activities performed outside of a spacecraft outside of the Earth’s atmosphere). Our group 3 project liaison is Daren Welsh, EVA Instructor & Flight Controller and avid wiki enthusiast.

## Slide 3: Project Overview
NASA EVA information is stored in a private wiki (MediaWiki)
MediaWiki allows for extensions to interact with wiki data
Wiki data can be used to gamify the user experience
Gamification can be used to increase wiki use and optimization
Notes: The NASA EVA information is presently stored in a series of private wikis on the MediaWiki open source platform (the same platform and company behind the popular Wikipedia website – one of the most recognized wikis in existence).
MediaWiki allows for third party extensions to be added to interact with preexisting and active wiki data.
This wiki data can be used to gamify the user experience and this gamification can be used to increase wiki use and allow for content optimization.

## Slide 4: What is Gamification?
Application of game-design features and concepts
Increases user engagement
  Competitively (group vs. individual)
  Cooperatively (team)
Examples
  Trophies
  Points
  Badges
Notes: [Victoria Guadagno]
Gamification is the application of game-design features and concepts with the intent of increasing user engagement. Wikis rely heavily on user engagement to add and maintain accurate information stored within the wiki and gamification is a tactic used to encourage this activity.
Gamification encourages competitiveness among groups and individuals to take and maintain a lead in any or all of the games available. Users can also work cooperatively as a team to bolster the wiki’s content base.
Some examples of gamification implementations are trophies with various versions depending on the amount of points obtained, points earned through a variety of means, such as making posts, and editing posts, or badges which can be earned at milestones, such as 100 posts, 100 edits, etc.

## Slide 5: Software Platform
MediaWiki (1.27.4)
  Meza install bundle (https://github.com/enterprisemediawik)
PHP (5.6)
MariaDB/MySQL (5.5.59)
Notes: The software platform installation is based on the client requirements which must adhere to the Meza install bundle located on GitHub which the NASA team uses. This means that specific versions must be used.
At the time of this presentation, the versions of software that required to be installed are:
MediaWiki (version 1.27.4)
PHP (version 5.6)
MariaDB/MySQL (version 5.5.59)
The Meza install also requires CentOS7, but for the sake of this project, because the cross-platform functionality of the software listed allows us to use various operating systems, we are using a Windows and Mac environments in addition to CentOS to ensure that we can more easily break the learning curve with familiar GUIs that are more comfortable and easier to interact with in the time allotted.
The Meza install also requires a set of extensions to be installed, but at this point, extensions will be installed in the project on an as-needed basis.

## Slide 6: Project Team
Victoria Guadagno – Documentation Lead
Okechukwu Ogudebe – Testing Lead
Jacqueline Macfadyen – Database Lead
Michael Salgo – Team Lead
Kevin Fortier – Lead Developer
Notes: [Jacqueline Macfadyen]
The team for this project consists of:
Victoria Guadagno, the documentation lead
Okechukwu Ogudebe, the testing lead
Jacqueline Macfadyen, the database lead
Michael Salgo, the team lead
And Kevin Fortier, the lead developer
Victoria will be responsible for all documentation. She will create most of the documentation and keep it updated.
Okechukwu will be responsible for all testing. He will create the test scripts, execute the test scripts, and create the test reports.
Jacqueline will be responsible for the database. She will lead all design discussions, document the design, and create the database creation script.
Michael will be responsible for managing the project, making sure that all tasks are completed on schedule and submitting all deliverables. He will be the main point of contact for both Dr. Brown and Daren Welsh.
Kevin will be responsible for all development. He will lead all design discussions and verify the documentation for the design.

## Slide 7: Project Scope
Build structure that can be built upon by future semesters
Develop
  Set of database tables
  User profile
  One game
Deliver
  Key project deliverables
  Handover documentation
Notes: During this semester we will build a structure that can be built upon by future semesters. We will develop a set of database tables, a user profile, and a single game. This will help future semesters towards the goal of a fully functional gamified system which is beyond the scope of this semester.
To aid development and future development, key project deliverables, such as a Project Charter, Project Schedule, and Project Management Plan, just to name a few, will be delivered to the project stakeholder (Dr. Brown) at the end of each of the four milestones in this project, submitting only documents that have been created or modified after the previous milestone documents were submitted for milestones 2 through 4. At the end of the fourth milestone, handover documentation will also be delivered to aid future teams in project work – reducing their learning curve that our team will have experienced. All deliverables will simultaneously be stored in GitHub for stakeholder visibility and project thoroughness.

## Slide 8: Milestone 1 – Define the Project
Start Date
  01/29/2018
End Date
  02/18/2018
Deliverables
  Project Charter
  Stakeholder Analysis
  Project Schedule
  Project Management Plan
Notes: [Kevin Fortier]
In milestone 1 we will define the project. Work for this milestone will start on January 29th and end on February 18th. Deliverables for this milestone will be the Project Charter, Stakeholder Analysis, Project Schedule, and the Project Management Plan.

## Slide 9: Milestone 2 – Design the Project
Start Date
  02/05/2018
End Date
  03/11/2018
Deliverables
  Requirements Document
  User Profile Design
  Game Design
  User Interface Design
  Database Design
Notes: In milestone 2 we will design the project. Work for this milestone will start on February 5th and end on March 11th. Deliverables for this milestone will be the Requirements Document, User Profile Design, Game Design, User Interface Design, and the Database Design.

## Slide 10: Milestone 3 – Development and Testing
Start Date
  03/09/2018
End Date
  04/01/2018
Deliverables
  Database Script
  User Profile Code
  Game Code
  Testing Reports for Database
  Database Documentation
  User Profile Documentation
  Game Documentation
Notes: In milestone 3 we will do development and testing. Work for this milestone will start on March 9th and end on April 1st. Deliverables for this milestone will be the Database Script, User Profile Code, Game Code, Testing Reports for the Database, Database Documentation, User Profile Documentation, and the Game Documentation.

## Slide 11: Milestone 4 – Handover Documentation
Start Date
  04/02/2018
End Date
  04/22/2018
Deliverable
  Handover Documentation
Notes: In milestone 4 we will complete handover documentation. Work for this milestone will start on April 2nd and end on April 22nd. The deliverable for this milestone will be the Handover Documentation.

## Slide 12: Project Caveats
System should be
  Open source
  Adhere to Meza installation
  Configurable
    Trophies vs. Medals
    Bronze, Silver, Gold vs. Sergeant, Lieutenant, Captain
    10, 100, 1000 points vs. 5, 50, 500 points
  Code will be managed via GitHub
    Separate accounts required
Notes: [Michael Salgo]
With this project come some caveats. The system that is developed must remain open source and must adhere to software versions installed by Meza. The system should be configurable so that users can call rewards different names, such as trophies or medals, assign a name to each threshold such as bronze, silver, gold or sergeant, lieutenant, captain, and even change the value of each threshold such as 10, 100, 1000 or 5, 50, 500.
Lastly, code will be managed via GitHub with each user required to have their own account to ensure proper branch operations are used.

## Slide 13: Q & A
Notes: This concludes our presentation and we open the floor up for any remaining questions.
[Q & A]
We thank you for your time, Dr. Brown, and this opportunity that you and the sponsor have provided. We look forward to our next presentation at the conclusion of this course.